## Sheet1
Project Name | Covid-19 Chatbot
Script Name | User Test Cases for Chatbot
Script Owner | Vishal Padma
Date | 2020-06-11
Test Case ID | Requirement | Scenario | Steps | Excpected Output | Output | Tested by | Date | Defect ID | Remarks
1 | 1- Main Index Page | 1- Check the main Page Visualization | 1. Navigate to the website using the link "" | Should be able to see load the website. | Website Loaded | Aditya
|  |  | 2. Navigate to the World Map section on the webpage. (In the start of the page) | Should be able to Navigate to the World Map on the webpage. | World map visualization loaded |  |  |  | Visualization loads slower than expected
|  |  | 3. Hover over any country to see the below details: a. Country b. CountryCode c. NewConfirmed d. NewDeaths e. NewRecovered f. TotalConfirmed g. TotalDeaths h. TotalRecovered i. CriticalCases j. Total Test k. DeathRatio l. RecoveryRatio | Should be able to see below details for any country details when you hover: a. Country b. CountryCode c. NewConfirmed d. NewDeaths e. NewRecovered f. TotalConfirmed g. TotalDeaths h. TotalRecovered i. CriticalCases j. Total Test k. DeathRatio l. RecoveryRatio | When hovering over a country, The information is diplayed clearly for each country.
2 | 1- Main Index Page | 2- Check the main Page Visualization | 1. Navigate to the website using the link "" | Should be able to see load the website. | Website Loaded | Aditya |  |  | Visualization displays clearly the relevant info required
|  |  | 2. Navigate to the Top 10 Countries who have most number of Conmfirmed Casaes section on the webpage. (In the Middle of the page) | Should be able to Navigate to the Top 10 Countries who have most number of Conmfirmed Casaes section on the webpage. | Top 10 Countries visualization loaded
|  |  | 3. Hover over any country to see the below details: a. Country b. Total Confirmed | Should be able to see below details for any country details when you hover: a. Country b. Total Confirmed | When hovering over each country, the name and the correspoinding stat is loaded
3 | 1- Main Index Page | 3- Check the main Page Visualization | 1. Navigate to the website using the link "" | Should be able to see load the website. |  | Apurva
|  |  | 2. Navigate to the Top 10 Countries who have most number of Recovered Casaes section on the webpage. (In the Middle of the page) | Should be able to Navigate to the Top 10 Countries who have most number of Recovered Casaes section on the webpage.
|  |  | 3. Hover over any country to see the below details: a. Country b. Total Recovered | Should be able to see below details for any country details when you hover: a. Country b. Total Recovered
4 | 1- Main Index Page | 4- Check the main Page Visualization | 1. Navigate to the website using the link "" | Should be able to see load the website. |  | Apurva
|  |  | 2. Navigate to the Top 10 Countries who have most number of Deaths Casaes section on the webpage. (In the Middle of the page) | Should be able to Navigate to the Top 10 Countries who have most number of Deaths Casaes section on the webpage.
|  |  | 3. Hover over any country to see the below details: a. Country b. Total Confirmed | Should be able to see below details for any country details when you hover: a. Country b. Total Confirmed
5 | 1- Main Index Page | 5- Check the main Page Visualization | 1. Navigate to the website using the link "" | Should be able to see load the website. |  | Apurva
|  |  | 2. Navigate to the Country-Wise Timeline Observed Cases section on the webpage. (In the end of the page) | Should be able to Navigate to the Top 10 Countries who have most number of Deaths Casaes section on the webpage.
|  |  | 3. Select any country from the list on the right to see diifferent cases. | Should be able to select country from the list on the right.
|  |  | 4. After selecting the country, the line grapgh should be updated. | Line graph should upgrade after the selection of the country.
|  |  | 5. Select anyone Category from the four categories listed(Confirmed, Recovered,Deaths and Active). | Should be able to select categories.
|  |  | 6. After selecting the category, other categories fades in the background. | After selecting the category, other categories should fade in the background.
|  |  | 7. Hover over ther line and statistics will be displayed. | When hovered over the line graph, statistics should be displayed.
6 | 2- Main Index Page For Ireland | 6- Check the main Page Visualization | 1. Navigate to the website using the link "" | Should be able to see load the website. |  | Ashwin
|  |  | 2. Navigate to the Ireland Map section on the webpage. (In the start of the page) | Should be able to Navigate to the Ireland Map on the webpage.
|  |  | 3. Hover over any country to see the below details: a. Country b. Case By Population c. Confirmed Cases d. Population | Should be able to see below details for any country details when you hover: a. Country b. Case By Population c. Confirmed Cases d. Population
7 | 2- Main Index Page For Ireland | 7- Check the main Page Visualization | 1. Navigate to the website using the link "" | Should be able to see load the website. |  | Ashwin
|  |  | 2. Navigate to the Trend observed in the Total number of Confirmed Cases and Deaths recorded over the period section on the webpage. (Second graph on the page) | Should be able to Trend observed in the Total number of Confirmed Cases and Deaths recorded over the period section on the webpage.
|  |  | 3. Select anyone Category from the four categories listed(Total Confirmed and Total Deaths ). | Should be able to select categories.
|  |  | 4. After selecting the category, other categories fades in the background. | After selecting the category, other categories should fade in the background.
|  |  | 5. Hover over ther line and statistics will be displayed. | When hovered over the line graph, statistics should be displayed.
8 | 2- Main Index Page For Ireland | 8- Check the main Page Visualization | 1. Navigate to the website using the link "" | Should be able to see load the website. |  | Minaz
|  |  | 2. Navigate to the Trend observed in the number of Confirmed Cases and Deaths recorded over the period section on the webpage. (Third graph on the page) | Should be able to Trend observed in the number of Confirmed Cases and Deaths recorded over the period section on the webpage.
|  |  | 3. Select anyone Category from the four categories listed(Confirmed and Deaths ). | Should be able to select categories.
|  |  | 4. After selecting the category, other categories fades in the background. | After selecting the category, other categories should fade in the background.
|  |  | 5. Hover over ther line and statistics will be displayed. | When hovered over the line graph, statistics should be displayed.
9 | 2- Main Index Page For Ireland | 9- Check the main Page Visualization | 1. Navigate to the website using the link "" | Should be able to see load the website. |  | Minaz
|  |  | 2. Navigate to the Trend observed in the number of Confirmed cases over the period section on the webpage. (Fourth graph on the page) | Should be able to Trend observed in the number of Confirmed cases over the period section on the webpage.
|  |  | 3. Hover over ther line and statistics will be displayed. | When hovered over the line graph, statistics should be displayed.
10 | 2- Main Index Page For Ireland | 10- Check the main Page Visualization | 1. Navigate to the website using the link "" | Should be able to see load the website. |  | Nripendra
|  |  | 2. Navigate to the Trend observed in the number of Deaths recorded over the period section on the webpage. (Fifth graph on the page) | Should be able to Trend observed in the number of Deaths recorded over the period section on the webpage.
|  |  | 3. Hover over ther line and statistics will be displayed. | When hovered over the line graph, statistics should be displayed.
11 | 2- Main Index Page For Ireland | 11- Check the main Page Visualization | 1. Navigate to the website using the link "" | Should be able to see load the website. |  | Nripendra
|  |  | 2. Navigate to the Total number of recored Confirmed Cases by County in ireland. (Counties with more than 400 recorded cases) section on the webpage. (Sixth graph on the page) | Should be able to Total number of recored Confirmed Cases by County in ireland. (Counties with more than 400 recorded cases) section on the webpage.
|  |  | 3. Hover over any country to see the below details: a. CountryName b. Confirmed | Should be able to see below details for any country details when you hover: a. CountryName b. Confirmed
12 | 2- Main Index Page For Ireland | 12- Check the main Page Visualization | 1. Navigate to the website using the link "" | Should be able to see load the website. |  | Sumit
|  |  | 2. Navigate to the Trend that shows the growth of the total number of infected cases of COVID-19 amongst different age-groups section on the webpage. (In the end of the page) | Should be able to Navigate to the Trend that shows the growth of the total number of infected cases of COVID-19 amongst different age-groups section on the webpage.
|  |  | 3. Select anyone Category from the categories listed(With different age group). | Should be able to select categories.
|  |  | 4. After selecting the category, other categories fades in the background. | After selecting the category, other categories should fade in the background.
|  |  | 5. Hover over ther line and statistics will be displayed. | When hovered over the line graph, statistics should be displayed.
13 | 2- Main Index Page For Ireland | 13- Check the main Page Visualization | 1. Navigate to the website using the link "" | Should be able to see load the website. |  | Sumit
|  |  | 2. Navigate to the Trend showing the total number of Hospitalized Cases in Ireland over time section on the webpage. (Sixth graph on the page) | Should be able to Trend showing the total number of Hospitalized Cases in Ireland over time section on the webpage.
|  |  | 3. Hover over ther line and statistics will be displayed. | When hovered over the line graph, statistics should be displayed.